| 2021 UGVR Program Timeline |  |
| --- | --- |
| Date | Tasks |
| Oct 15, 2020 | UGVR program announcement to SU faculty |
| Nov 10, 2020 | SU PM collects position descriptions from host faculty and sends to partner universities. |
| Dec 30, 2020 | Partner universities collect applications and pre-select candidates. Each school chooses up-to-3 students for each position and sends applications to SU PM. |
| Feb 5, 2021 | SU faculty members review applications and make final admission decisions. SU PM coordinates the process and sends selection results to partner universities. |
| Feb 28, 2021 | Students make decision and give acceptance confirmation. Partner universities collect application forms and passport copies and submit to SU PM. |
| March 5, 2021 | SU PM prepares official invitation letter and submits application packages to Registrar’s Office for approval. SU PM sends DS-7002 forms for confirmed students to sign. |
| April 25, 2021 | SU PM obtains SU ID#s for UGVR students. Submit application to Bechtel for SEVIS DS-2019 forms. Send UGVR students official invitation letters, DS-2019 forms, and DS-7002 forms. |
| May - June 2021 | Student apply for US visa. SU makes travel arrangement and logistics. Partner university/ Students arrange wire transfer per invoice. |
| June 28 -Aug 31, 2021 | UGVR students conduct summer research at Stanford |
| Sept 30, 2021 | SU PM coordinates and helps with program certificate letters. Collects boarding passes and other required docs from the students. Conduct program survey with participating faculty and students. |